## Wedding Timeline (Prep)
Wedding of Raymond Wee and Jannes Tan
Wedding Preparation (Exclude Honeymoon Preparation)
Date of Actual Day: …
Venue of Banquet: Furama RiverFront Hotel
Name and contact of Banquet Catering Sales Manager:
Address of Banquet:
Bridal Shop, Name and contact of Manager: Sattine, Kelvin Khee, 62212293/91850121
Photography and Videography: Coffee and Tea Dreamworks, Fion Tay, 63371714, Email: production@dreamzcoffee.com
Photographer: 6am to 11.30am, 7pm to 12.30am, Videographer: 6am to 11.30am, 7pm to 12.30am
Rev date: 1 Jun 2009
S/N | Task | Timeline | Action by | Status/Remarks
12 months before Actual Day (...)
1 | Locate & book banquet venue | 2008-06-01
9 months before Actual Day
1 | Confirm brothers' and MCs availability
2 | Check package for videographer and photographer (including a comic version of our love life)
3 | Consult with wife about budget
4 | Confirm sisters' availability
5 | Schedule fittings for bridal attire Depends on delivery dates of attire
6 | Begin guest list - get apx. head count
7 | Draft and finalise Storyline, photos and songs for all videos (Coffee and Tea Dreamworkz)
8 | Confirm Bridal Car
5 months before Actual Day
1 | Make groom's shoes
2 | Collect Bride's shoes
3 | Pick bridal accessories, veil, shoes, etc.
4 | Tuxedo rentals & fittings for groom
5 | Have a trial on both hair and make-up
6 | Do studio and outdoor photoshoot
7 | Get map to banquet venue, to include in invitattion card
8 | Get moscot for invitation card (from Dreamworkz)
9 | Design invitation cards
10 | Discuss about An Chuan and Guo Da Li and all wedding matters with parents of both sides
3 months before Actual Day
1 | Order invitations cards
2 | Do up maps and directions for out-of-town guests Include with invitations
3 | Consult geomacy on details for An Chuan and Guo Da Li
4 | Book schedule for food tasting (19 Apr 09)
5 | Confirm food tasting date
6 | Select Photos
7 | Make appointment with hairstylist (bride)
8 | Finalize guest list - compile addresses
2 months before Actual Day
1 | Call to print invitation cards
2 | Parents to discuss and finalise wedding details
3 | Do final preview to wedding photos
4 | Food tasting and confirm dishes
5 | Confirm no of cakes for relative
6 | Collect invitation cards
7 | Write invitation cards
8 | Send out invitation for online friends
9 | Send out invitation to local guests
10 | Send out invitation cards for Malacca relative by Registered post
11 | Send out email invitations and compile address of guests
12 | Follow up on video works
13 | Confirm Master of Ceremony
14 | Confirm Brothers and sisters
15 | Finalize guest list
16 | Order wedding cake
1 months before Actual Day (May 09)
1 | Send out invitation to overseas guests
2 | Confirm no of hotel rooms for overseas guests
3 | Advice our overseas guests to update passports, visas, inoculations, etc.
4 | Confirm both local and overseas guests have received invitation (RSVP)
5 | Confirm script for Master of Ceremony
6 | Apply for increase in credit limit from banks
7 | Finalise all cartoon production works
8 | Collect video works
9 | Collect studio photo album
10 | Brothers and sisters briefing and gathering
12 | Arrange for Mei Ren to visit new house
13 | Distribute Wedding invitation card
14 | Booking of Hotel rooms for Malaysia relatives
15 | Do up Photo collage
16 | Confirm Photos to be displayed
17 | Prepare Ang Baos
18 | Hire Lunch caterer and select menu
19 | Confirm number of muslim and vegetarian set for Banquet
20 | Plan reception, decorations, theme, etc.
21 | Confirm no of tables with Banquet
22 | Confirm wedding favours (Prepare extra)
23 | Confirm details with florist bouquets, boutonniere's, mothers'/fathers' corsage
24 | Try out all VCDs and DVDs at Banquet venue
25 | Confirm Banquet Operation Manager
26 | Work out traffic and parking issues
27 | Plan for wet weather programme
28 | Select theme for banquet stage
29 | Confirm that wedding gowns and suits will be ready on time
30 | Ensure that Chinese Characters are included in the menu
31 | Do up items for Guo Da Li
32 | Guo Da Li
1 week before Actual Day
1 | Final dress, headpiece & all clothing fitting
2 | Hairstyle, makeup, headpiece trial run
3 | Father-in-law final fitting and collection
4 | Pick up rental wedding attire (Earlier can't hurt; no surprises.)
5 | Confirm accommodations for out-of-town guests
6 | Call expected guests who haven't responded
7 | Rent out 3 suits and 1 pants (1 for FIL with pants, 2 for 2 brothers)
8 | Confirm Brothers and sisters again
9 | Confirm AD banquet's programme
10 | Confirm all flowers arrangements
11 | Call or sms potential guests
12 | Plan liquor needs
13 | Plan table numbering
14 | Confirm MC and MC script
15 | Pack 2 x photo player into Groom's pack
16 | Discuss rehearsal dinner with wife
17 | Groom & bride get hairdo
18 | Arrange rehearsal dinner
19 | Confirm rehearsal plan with officiant & attendants
20 | Buy poppers
21 | Arrange with banquet coordinator on assigning Chinese waiter/waitress for relative tables
22 | Break in bridal shoes - wear around house (Don't want sore feet …)
23 | Break in groom shoes
24 | Confirm transportation plans again
25 | Prepare wedding speech
26 | Make photographer list of pictures you want taken
27 | Confirm wedding car (Get driver's contact, confirm pick up time, bride parents pick up to and from bride house)
28 | Confirm photographer and videographer
29 | Pass the sis hand band to sis
30 | Collect 2 boxes of cakes, 2 packs of biscuits and 16 oranges
31 | Prepare Phototaking sequence
32 | Confirm Songlist for banquet
1 day before Actual Day
1 | An Chuan
2 | Fetch Mum to hairdo
3 | Review duties with wedding participants
4 | Review seating details
5 | Prepare to Sing a Song
6 | Last minute details with all service providers (Banquet, videographer, photographer, bridal car)
7 | Collect flower and 6 cosages from Sattine
8 | Pack all bride's clothes (To be carried around the next day)
9 | Pack all groom's clothes (To be carried around the next day)
10 | Check on bridal car deco
11 | Buy Breakfast
12 | Fetch Malaysia Relative to Hotel
13 | Call bridal car driver and go through the way to groom's house. Esp important if groom's house is new and not in the street directory.
14 | Relax!

## Wedding Timeline (AD)
Wedding of Raymond Wee and Jannes Tan
Order of Proceedings on Actual Day
Date of Actual Day: |  | Bro's Name | Contact | Sis's name | Contact
Venue of Banquet:
Address of Banquet:
Bridal Car Driver:
Bridal Shop, Name and contact of Manager:
Photography and Videography: Coffee and Tea Dreamworks, Serene, 63371714, Coffee Tang (Photographer): 81230352, Terry (Videographer): +60167171852
Photographer: 5.30am to 11.30am, 7pm to 11.30pm, Videographer: 5.30am to 11.30am, 7pm to 11.30pm
Rev date: 6 Jun 2009
S/N | Task | Timeline | Action by | Status/Remarks
Briefing to all coordinators
1 | Coordinate the dress colour of bros and sis (Bro: Pink top and black or dark brown pants, Sis: Cream) (For morning only) (Evening gown for ladies and Shirt & (Tie or suit) for gentlemen)
11 | Arrange two to handle logistics (aka Logistics Officers)
2 | Arrange for day 2 chief programmers to manage the day programme. - Bros also to help check the path to be cleared before Groom and bride approach.
12 | Assign 1 to help in opening new house door
3 | Arrange 1 sis to coordinate Tea ceremony at Bride's house
4 | Arrange 1 bro to coordinate Tea ceremony at Groom's house
5 | Wedding rehearsal
3 | Arrange bros and siss to handle poppers and flower pedals
4 | Arrange Yam Seng party
10 | Yam Seng Coordinator
2 | Arrange one or two to drink!
8 | Assign one to monitor free flow beer, red & white wine and hard liquor
9 | Arrange 3 brothers to coordinate photo taking, table-by-table
13 | Assign 1 or 2 to help in money management for banquet
14 | Assign two to bring up Ang Baos to room before start of banquet
Transportation Plan (Morning Ceromony)
1 | Bridal car
2 | Car 1
3 | Car 2
4 | Car 3
5 | Car 4
6 | Car 5
Logistics list
S/N | Item(s) |  | Action by
Morning
1 | Red Ribbons for Drivers (6 sets)
2 | MicPro (1 set)
3 | Towel for Groom in the morning
4 | All receipts and contracts
Just before leaving new house for Parents-in-law house in the afternoon
1 | Make-up and accessories boxes
2 | Bridal clothes
3 | Shampoo and all bathing stuff
4 | 5 corsages from new house's fridge
5 | Poppers
6 | Hard Liquors
7 | Guest Book
8 | Pens of different colours
9 | 2 Red packet boxes
10 | All DVDs (March-in song, 2nd march-in song, cartoon video, Montage Part 1, Montage Part 2, Photo Animation & Other songs)
11 | Music CDs (Reception, after 1st March-in, after 2nd March-in)
12 | 2 Digital Photo Frames
13 | Precious Moment Photo Album
14 | Studio Photo Album
15 | All Ties
16 | 2 small bags (to put all Red packets in the evening)
17 | Flower pedals |  | Banquet Mgr
Actual Day (...)
1 | Bride wake up | 4am
2 | Bride take light but nutritious breakfast | 4.15am
3 | Arrival of make-up artist at bride's place | 4.20am
4 | Bride make-up | 4.30am
5 | Groom wake up | 5am
6 | bros wake up | 5am
7 | Bride give make-up artist a red packet | 5.20am
8 | bro start off from Groom's house to fetch Mei Ren | 5.20am
9 | Arrival of videographer & photographer at Bride's house | 5.30am
10 | Groom take light but nutritious breakfast | 5.30am
11 | Bro reach Mei Ren's house | 5.45am
12 | Arrival of all brothers and sisters, at house respectively (Sis ready by 6.15am) | 5.45-6am
13 | Arrival of Mei Ren | 6am
14 | Arrival of bridal car & driver at Groom's house | 6.10am
15 | Final briefing to brothers/sister (by Groom & bride respectively) | 6.10am
16 | Groom give out ribbon for all drivers | 6.15am
17 | bro call parents-in-law that we are moving off | 6.25am
18 | Groom leave house to Bride's house (Going to carpark from Tampines Main Road) (Mei Ren to carry 8 oranges, 2 cake, 8 pork cans, 2 types of biscuits, 1 red packet) (Groom to take Hand Flower and put on 1 corsage) | 6.30am
19 | Groom reach Bride's house | 6.40am
20 | Boy opens door for Groom | 6.45am
21 | Groom gives red packet to boy | 6.45am
22 | Groom's gatecrash | 6.50am
| Groom enters room to Bride - Groom gives hand flower to Bride - Groom uncover veil of Bride and kiss her | 7.35am
23 | Groom & Bride eat wedding item | 7.45am | These are mostly done after groom side tea ceremony, at step 52 as below.
24 | Tea Ceremony at Bride's house - 1 sis to coordinate with Mei Ren (To ensure photographer and videographer can capture the best moments) | 7.55am
25 | Photo Taking | 8am
26 | Groom gives red packet to all children | 8.15am
27 | Parents-in-law gives red packet to videographer and photographer | 8.15am
29 | Gathers all bros, ready to move off | 8.20am
30 | Bride & Groom proceed to Groom's house | 8.25am
31 | Bride to remember to throw the Fan from car | 8.25am
32 | bro call Raymond's mum to inform her that we are moving off to her venue | 8.25am
33 | Bride & Groom reach Groom's house | 9am
34 | Boy opens door for Bride | 9am
35 | Bride gives red packet to boy | 9am
36 | Tea ceremony at Groom's house (bro to coordinate with Mei Ren so as to ensure photographer and videographer can capture the best moments) | 9.10am
37 | Groom & Bride eat wedding item | 9.30am
38 | Groom give Red Packet to Brothers | 9.30am
39 | Bride and Groom gives red packet to all unmarried guests | 9.30am
40 | Photo-taking at Groom's house | 9.35am
41 | Morning Tea break at Raymond's parent house | 10am
43 | Gathers all bros, ready to move off | 10am
44 | Proceed to new house | 10.30am
45 | bro turns on all lights in new house | 11am
46 | bro opens door for Bride and Groom | 11am
47 | Videographer and photographer take Bride and Groom's photo and video | 11.10am
48 | Videographer and photographer leaves to edit video | 11.30am
49 | Bride change to Qua dress | 11.30pm
50 | Load all logistics to car 1 | 11.40am
51 | bro to call parents-in-law that we are going over | 11.50am
52 | Bride & Groom proceed to parents-in-laws' house | 11.50am
53 | Lunch at Bride's house | 12noon
54 | All bros & siss leave for home to rest and change. | 12-1pm
55 | Proceed to Groom's house | 1pm
56 | bro call hotel the estimated arrival time (call 30 mins in advanced) | 1.15-1.30pm
57 | Light food at Groom's house | 1.30pm
58 | Proceed to Banquet venue | 1.45pm
59 | Groom give Red Packet to driver when reach hotel | 1.45pm
60 | Rest for all | 2-4pm
Actual Day (..., 4pm)
1 | Junliang set off from hotel to fetch 6 relatives from Jannes's house to hotel | 5pm
2 | Junliang to call Jannes's parents to inform them the estimated time of arrival | 5pm
3 | Arrival of Emcees at Bridal room | 5pm
4 | Discussion with Banquet Manager and DJ | 5pm
5 | Bridal car set of from parents-in-law place to banquet venue (Junliang fetch Aunties) | 5.30pm
6 | Arrival of Make-up artist at hotel | 5.30pm
7 | Bros & Siss arrive in hotel | 5.30pm
8 | Rehearsal starts for Banquet Manager, DJ, Emcees and Raymond | 5.30pm
9 | Final Briefing to all brothers and sisters on their roles - Brief on activation of poppers - ToDo List | 5.30pm
10 | Parents-in-law meet Jannes's relatives at the Hotel Restaurant | 5.30pm
11 | Ensure champagne is ready | 5.30pm
12 | Ensure cake knife is present | 5.30pm
13 | Ensure correct number of banquet tables | 5.30pm
14 | Play through all videos and photos | 5.30pm
15 | Label the VIP table | 5.30pm
16 | Parents-in-law and Jannes's relatives arrive at Hotel | 6pm
17 | Junliang fetch Jannes relatives to Hotel restaurant (The Square) - Junliang call Raymond | 6pm
18 | Raymond fetch parents-in-law to Bridal suite to make-up | 6pm
19 | Setup guest list, ang bao boxes and carpark card | 6pm
20 | Set up photo gallery corner | 6pm
21 | Final check through of all tables and wedding favours | 6pm
22 | Arrange poppers and flower pedals at table near march-in path | 6pm
23 | Arrival of videographer and photographer | 7pm
24 | Check through morning tea ceremony video | 7pm
25 | Refer to Banquet Proceedings | 7.30pm
Actual Day (..., 12mid)
1 | Pay balance due to service providers (some may require earlier payment)
2 | Parents-in-law take bridal car home | 12.15-12.30am
After the wedding (within 1 months)
1 | Deposit money to bank
2 | Return items that are on loan or hired as soon as possible
3 | Pay credit card bills

## Scripts for Emcees
Wedding of Raymond Wee and Jannes Tan on ……
Order of Proceedings for Banquet on Actual Day
Time | Emcee | Contents
7.00pm | - | Arrival of guest and start of cocktail reception.
7.30pm | - | Guests make entrance to ballroom.
Play and loop Photo Animation
Mervyn brief all guests who are near the march-in path to use poppers during 1st March-In
8.15pm | English | A very good evening to all the beautiful ladies and charming gentlemen. I'm ... and this is my partner .... On behalf of ...... and ......, we would like to thank all of you for being here to share this joyous occasion with us. Please take a seat as the dinner will commence shortly.
| Chinese | 各位来宾,大家晚上好. 今天是...幼男….与…...的千金…….的大喜日子. 非常感谢各位今晚出席他们的结婚喜宴．我是…..., 在我身边的是…….. 我们将是今晚的司仪．在此请各位就座, 喜宴即将开始．
8.20pm | English | Ladies & Gentlemen, I believe you guys will like to know how ... first got to know ……., how he courted her and how he proposed to ….... So …... and ……. have produced a wonderful animation to share their love story.
| Chinese | 各位来宾，想信大家都很好奇…...与…...如何相识,相知到相恋. 为了这美满的结合,他们制作了一段动画来述说他们的爱情故事.
| English | Please sit back, relax and enjoy.
Lights dim, play cartoon animation
All bros and siss form 2 lines along March-In path with poppers and flower pedals. Activate poppers and throw flower pedals during march-in.
8.28pm | English | We hope you've enjoyed the animation. Tonight is indeed an occasion we've all been looking forward to, especially for ....... and ......., who are at this very moment waiting to make their grand entrance. Without further ado, let us all rise and give our warmest welcome to our newly weds!
| Chinese | 各位来宾,相信这是我们期待已久的时刻.请大家起立,让我们以最热烈的掌声来欢迎这对新人入席.
First march in with music until both went on stage.
8.33pm | English | The newly weds will now proceed to the cake cutting ceremony. Let's wish the couple a sweet, creamy and smooth blissful marriage.
| Chinese | 在这喜庆的日子里，新郎和新娘将共同切开一个洁白的百年好合婚礼大蛋糕，这象征着他们对爱情永恒的宣誓和为未来美好新生活剪彩。 洁白芬芳的蛋糕，香甜纯美，也象征着他们的婚姻甜甜蜜蜜，幸福美满。
After cake cutting and couples take their seat at VIP table.
8.35pm | English | Thank you …… & …….. Please sit back and enjoy this lovely evening. Dinner shall be served shortly.
| Chinese | 谢谢，请各位就坐。晚宴即将开始，请尽情享用！ 在此呢，送我们在座的所有来宾一副对联。上联是：吃，吃尽天下美味不要浪费，下联是：喝，喝尽人间美酒不要喝醉，横批就是：吃好喝好！如有怠慢之处，还请大家多多包含。
Lights dim and music plays. First dish comes in.
Show Wedding Studio Indoor and Outdoor Photoshoot (1st Photo Montage)
When second dish is served, couples go to change and prepare for second march in.
Once couple is ready at waiting area, Emcees go on stage.
9.15pm | English | I hope you have enjoyed your dinner so far. The sisters have a great time this morning teasing the brothers and ....... is trying all means to convince the sisters to open the door to ........ We have captured all these to share the exciting moments with you.
| Chinese | 希望大家对今晚的宴席还感到满意。现在让我们一起分享一下今早迎亲的喜悦片段，究竟姐妹们是如何整哥儿们的呢，尽请观看。
Play Express Clip
After the Express clip and couple ready for second march in.
9.20pm | English | I believe you all have enjoyed the video very much. Tonight is indeed a memorable night for …... and …….. So let's put our hands together again to welcome the groom and bride for the champagne pouring ceremony.
| Chinese | 看来大家对刚才播放的迎亲片段中姐妹们的行为十分满意，看得出大家都乐在其中，而今晚也的确是我们的新人最最难忘的一晚，现在请大家举起金掌银掌发财掌，再次以最热烈的掌声欢迎新郎新娘入场举行倒香槟仪式。 （新人上台后）从一个人的精彩到两个人的世界，在今晚，我们两位新人终于走到了一起。晶莹的香槟美酒在水晶杯塔之间缓缓流淌，就像我们两位新人把他们的心，把他们的情，交于对方，混合交融。（看情况发挥啦）在今天，在这么一个喜气洋洋的日子里，让我们深深的祝愿你们俩，祝福你们俩，用你们的双手，勤劳的双手，去开创一片洁净而又美好的天地，用你们的双手，勤劳的双手，去共筑一个浓情蜜意的爱巢，去开创美好的未来。
Second march in till both went on stage. Couple proceed to Champagne pouring and Yam Seng.
9.25pm | English | With entwined arms and a loving toast, let's all toast to their happy marriage.
| Chinese | 我们现在有请这对新人喝交杯酒。这满满的交杯酒是我们两位新人，用他们的情，用他们的爱酿造的美酒，也只有真心相爱的人，才能喝的美酒，喝了这杯酒，今生今世不分手。祝福这对新人新婚愉快、白头偕老、永结同心！
9.30pm | English | Ladies & Gentlemen, our favourite segment of this banquet is here. We will like to invite the immediate family members with all the brothers and sisters up on stage for the Yam Seng toast. 1st Yum Seng: wishing them a blissful marriage 2nd Yum Seng: wishing them everlasting love 3rd Yum Seng, to be the loudest & longest: to have Baby Raymond and Baby Jannes
9.40pm | Chinese | 在此，让我们邀请新人吉庆、锦帆与双方家长，姐妹团与兄弟团们上台来进行敬酒仪式。 请各位站起来举起手中的杯，以三声Yamseng来祝福这对新人： 第一声，祝福他们俩永浴爱河；Yamseng 第二声，祝福他们百年好合；Yamseng 第三声，祝福他们早生贵子——最好是生龙凤双胞胎。Yamseng
After Yum Seng.
Speech by Groom
Speech by Bride
10pm | English | Thank you and let's give them one more round of applause.
| Chinese | 谢谢各位，我们再次以热烈的掌声祝福他们。祝愿您们的生活象蜜糖般甜蜜；你们的爱情象钻石般永恒；你们的事业象黄金般那样灿烂。也愿各位来宾分享这天伦之乐，度过美好的时光。
| English | Thank you very much, please enjoy your dinner.
| Chinese | 谢谢大家，请大家继续享用美味佳肴。
Play 2nd Photo Montage and songs
Dinner continues. Couples proceed with parents on photo taking from table to table. See phototaking sequence.
After Phototaking, Bride change to Qua. (By 10.45pm - By 6th dish)
Both parents, Groom and Bride wait at entrance to thank guests. (11pm)
11.30pm | English | Dear guests, we have now come to the end of the wedding banquet. Thank you all very much for your presence tonight. We hoped you have all enjoyed the dinner and may you have a pleasant evening. Thank you!
| Chinese | 今晚的婚宴已到了尾声，非常感谢您的莅临，与浓情厚礼，祝各位晚安！最后我代表两位新人再次对各位嘉宾的到来表示感谢，并真诚的祝愿大家今晚良宵美满，祝愿大家今后的生活一帆风顺、两全其美、三羊开泰、四季平安、五福临门、六六大顺、七星高照、八面聚财、九九（久久）安康、十全十美、百事可乐、千事吉祥、万事如意。

## Actual Day Wedding
Wedding of Raymond Wee and Jannes Tan
Wedding Budget
S/N | Purpose | Value Per pax | unit | Total | Remarks
Before Wedding Day
1 | Wedding Cake |  | 10 | 0 | For relatives
2 | Invitation Card |  | 120 | 0 | Include printing and postage
3 | Hotel Rooms |  | 9
4 | Studio |  | 1 | 0
5 | Additional for Studio |  | 1
6 | Videography & comic |  | 1 | 0
7 | Bride's shoes |  | 1
8 | Groom's shoes |  | 1
Traditional Ceremony
1 | Red Packets |  |  | 0 | For Brothers (More for Chief Brother)
2 | Red Packets |  |  | 0 | For Jannes's sisters
3 | Red Packet |  |  | 0 | For opening car door at Jannes side
4 | Red Packet |  |  | 0 | For opening car door at Raymond side (Given by Jannes)
5 | Red Packets |  |  | 0 | Bridal car Driver
6 | Red Packets |  |  | 0 | Others (Photographer, Videographer, Make-up artist)
7 | Red Packet for MCs |  |  | 0
8 | Red Packets for unmarried |  |  | 0
9 | Other Red Packets |  |  | 0
10 | Bride's Price |  |  | 0
11 | Pork Can |  |  | 0 | To Jannes's Parents
12 | Buffet (lunch) |  |  | 0 | At Raymond's parent house
13 | Buffet (lunch) |  |  | 0 | At Jannes's parents house
Sub-Total |  |  |  | 0
Dinner
1 | Banquet |  |  |  | 2 spare tables
2 | Deposit paid for banquet |  | 1
Total |  |  |  | 0

## Custom Proceedings
Wedding of Raymond Wee and Jannes Tan
Wedding Preparation
S/N | An Chuang on … |  | S/N | Guo Da Li on …
| Things to Buy: | Quantity |  | Groom (All items to paste Double Xi): | Quantity | Total to buy
| Small Double Xi Plate |  | 1 | Pig trotters can (bride return some) | 8 cans | 20 cans
1 | Longans | 2 packs | 2 | Red packet containing Bride Price (bride to return a small token)
2 | Red Dates | 2 packs | 3 | Liew Li/Man Tang Hong (Red Packet)
3 | Lotus Seeds | 2 packs | 4 | Cakes (bride to return 4 to groom) (For distribution to relative and for praying.) | 8 boxes | 14 boxes
4 | Bai3 He2 | 2 packs | 5 | Martell | 2 bottles | 2 bottles
5 | Red Packets ($8): 2 on plate and 1 per corner of bed | 6 | 6 | Long2 Feng4 Zhu2 (groom takes phoenix and bride takes dragon) | 1 pair | 1 pair
6 | Oranges | 2 | 7 | Oranges (Bride to return 8) | 28 | 46
|  |  | 8 | Mah Lao | 1 pair | 1 pair
| Procedures to Follow: |  | 9 | Mee Lao | 1 pair | 1 pair
| 1) Boy roll on bed after the bed is positioned and all the above items are placed on bed. |  | 10 | Gold Hand Bracelet (Bought by Raymond) | 1 pair | 1 pair
| 2) Groom's mother give Ang pow to boy rolling on bed. |  |  | Big basket (for groom to put things in, for bride to put things in for return then groom carry back home) | 1 | 1
| 3) Bride's parents give Ang pow to boy rolling on bed. |  |  | Ang pow for match maker (To be given by Raymond's mother) | 1 | 1
| 4) After An Chuang, nobody supposed to enter the master bedroom from then onwards, only couple allowed. But no sleeping on the bed. |  |  | No of tables for Jannes's parents: (for Jannes relative and colleagues)
| 5) Xi plate with longans, etc leave on bed for 12 days. |  |  | Bride (All items to paste Double Xi):
| 6) Boil water with longans, etc and drink after 12 days. If fall short of 12 days, leave plate aside and boil with water once 12 days is up after customary. |  | 1 | Red Packet (Returned small token from Bride's price)
| 7) 6 ang pows keep, don't use money inside. |  | 2 | Pig trotters can (Return from Groom's gift) | 4 cans
|  |  | 3 | Green Banana "Che Ge Jio" (To pray to Tien Gong) - hokkein custom | 1
|  |  | 4 | Cakes (Return from Groom's gift) | 4 boxes
|  |  | 5 | Gek Bian (kind of cake) (12 pieces in a box) | 1 pack
S/N | Customary on … |  | 6 | Khe Giau | 1 pack
|  |  | 7 | Red Dates | 1 pack
| Groom: | Quantity | 8 | Oranges (Return from Groom's gift) | 8
1 | Pig trotters can | 8 cans | 9 | Peanuts | 1 pack
2 | Oranges | 8 | 10 | Orange drinks in plastics bottle (tie top and bottom together using red ribbon) (In exchange for the Martell) | 2 bottles
3 | Cake | 2 | 11 | Liew Li (Red Packet) | 220
4 | Red Packet | 1 | 12 | Fong Candle | 1 set
| Red packets for ah yees |  |  | Ang pow for match maker (To be given by Jannes's parents) | 1
| Red packet for driver (bigger than bride side) |  |  | New items for Bride and Groom New house (given by Bride's parents) (Can be bought from Wedding Shop)
| Red packets for brothers |  | 1 | Double Xi lamps (either battery operated or electrically perated) | 1 pair
| Red packet for any small kids following |  | 2 | Comforter Set, Blankets, Pillows for bride, bed sheets, bolster (tie together using ribbon) - Used for An Chuang | 1 set
| Red packet for photographer |  | 3 | Suitcase to put bride's clothes | 1
| Red packet for videographer |  | 4 | Baby Bath Pail | 1
| Red packet for kid opening car door |  | 5 | Face basin (with double Xi word on it) | 1
|  |  | 6 | Xi stickers (include 2 big ones to paste master bedroom door and main wooden door, small ones to paste everything)
| Bride: |  | 7 | Ruler
| Red packets for ah yees |  | 8 | Ribbons (3 different sizes, big one to tie pillows)
| Red packet for driver |  | 9 | Fans (1 for use on Actual Day and 1 for throwing from car) | 2
| Red packet for makeup artist |  | 10 | Home slippers | 2
| Red packet for any small kids following journey |  | 11 | Spittoon (baby use later, small and plactic type) | 1
| Red packet for brothers |  | 12 | Sewing Box with 6/8/12 rolls of threads + needles + scissors (scissors dun use for cutting so soon) | 1 set
| Red packet for videographer |  | 13 | Comb | 2
| Red packet for photographer |  | 14 | Mouth rinse container | 2
|  |  | 15 | Yuan | 3 packs
| From Raymond's mother, when Bride and Groom go back to Jannes's house: |  | 16 | Red strings | 1 pair
1 | Bian (About 4 pcs per box) | 2 box | 17 | Towels | 2
2 | Red Packet | 1 | 18 | Toothbrush | 2
|  |  | 19 | Toothpaste | 2
| From Jannes's mother, when Bride and Groom go back to Raymond's house: |  | 20 | Red umbrella | 1
1 | Red Packets (in place of sugarcane and chicken) | 1 |  | A few things missed above…I advise you to visit those shops selling wedding stuff in Chinatown market.
2 | Bian (About 4 pcs per box) | 1 box

## Banquet Venue
Raymond & Jannes Actual Day Wedding Venue List
http://www.singaporebrides.com/banquets.htm
S/N | Venue | Min (Max) tables | Cost per table | Date | Contact No | Contact Person & Designation | Email | Website | Address
1 | Furama RiverFront (Venus Ballroom) | 30 (55) |  |  |  |  | riverfront@furama.com | http://riverfront.furama.com | 405 Havelock Road Singapore 169633
Typical Terms and conditions 1. Set of 8 course Chinese Menu 2. Complimentary one or two nights stay in the hotel suite, with buffet breakfast for 2 persons 3. Complimentary bottle of champagne, fruit basket and breakfast for two 4 Complimentary parking for up to 20% or 30% of confirmed attendance 5. Complimentary 1 30/40L barrel of beer 6. Complimentary trial dinner for 6 or 10 people 7. Complimentary wedding favours for all your invited guests 8. Free flow of Chinese tea, soft drinks and mixes (not inclusive of juices) 9. Wedding invitation cards with envelopes based on 60% or 70% of confirmed attendance (not inclusive of printing) 10. Free table(s) for every 20/30 tables 11. Pre-function area for welcome cocktail, with butler-passed snacks for guests 12. Multi-tier model wedding cake with top tier real cake for cake cutting ceremony 13. 5/6 tier champagne fountain with 1 complimentary bottle of champagne for Couple's toasting 14. Seat covers for all chair, with special setup for 2 VIP tables 15. Choice of Elegant Wedding floral decorations 16. Atmospheric dry ice effect for Bridal March in 17. Guest Book 18. Free usage of High Resolution LCD projector with screen and stereo sound system 19. Waiver of corkage charge for all wines and spirit liquor 20. 1 VIP lot for Bridal Car at Hotel entrance *21. Choice of menu *22. Special room rate for guests who wish to stay with us *23. $60/80 nett credit for room service in Bridal suite *24. One Day Room for wedding coordinators (2-8pm) *25. Complimentary Couple Spa package *26. Muslim and vegetarian menu for respective guests *27. 2 Free Ang Bao Box